## Part B - Final Risk Register
Project Risk Register | Team: 6
Project Manager Name: Oshoriame Olorife
| Risk Statement |  | Probability | Impact | Exposure
Risk Identification | Condition | Consequence | (%) | ($) | ($) | Mitigation | Contingency | Triggers | Assignee
Briefly describe the identified risk | Capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans. | Capture the result of the risk, should it happen. | Estimate of the probability the risk will occur. (use this probability in your Monte Carlo Analysis) | Estimate of the amount of impact or severity of the risk. (use this as worst case in Monte Carlo) | Probability x impact in $. Sort by this column to prioritize biggest $ risks. (use this as most likely case in Monte Carlo) | Document plans to lower the probability or to lower the impact ahead of time. | Identify what would have to be done if the risk were to become reality. | Identify what would prompt you to execute the contingency plan. | Identify who is responsible for tracking this risk and its changes in probability and impact. The assignee is not necessarily the person responsible for solving the problem, as risks often require escalation outside the team.
Technology (Technical/Scope) | Additional design and testing of the innovative technology | Schedule delay and cost. | 12% | 75000 | 9000 | Research and literature review. Contacting the product manufacturer and procuring their representative | Outsource an expert or choose an alternative technology. | If the technology becomes non-reliable, impractical, or inoperable. | SC
External Sources (Client/Stakeholder) | Client too involved in the process. Receiving pressure from stakeholders. | Schedule delay, costs incurred, lack of Standard of Care. | 8% | 10000 | 800 | Maintaining communication and managing clear expectations | Continue to have meetings with client, stakeholders/agency in order to discuss project schedule and plans. | Major conflicts with client regarding project ideas, design, and deliverables | PM
Contractual | Fixed price contract on a project that has many uncertainties. | Indemnification. | 10% | 25000 | 2500 | Establish clear language in the contract for the Scope of Work and potential changes. | Change the plan to be more cost effective if indemnification unavoidable. Refer the Client to the agreed Scope of Work in the Contract otherwise. Consult a lawyer. | If something was requested outside the scope of work. Receiving continued pressure from stakeholders. | PM
Personnel (Staff/Resources) | Staff not available. (Key hydrologist and senior staff for QC) | Schedule delay and cost. | 15% | 30000 | 4500 | Hire more experienced staff who are available to dedicate time to the project. Assess staff's strength and weaknesses, develop CPM, and implement appropriate PM methodologies | Organise workshop and training for staff. | Hired staff not available at critical parts of the project. New designer showing lack of progress or incompetency. | SC
Safety | Harmful effects of exposure to trichloroethylene. | Health threats to staff. Cost of liability. | 10% | 25000 | 2500 | Providing proper site safety guidelines, PPE for field observation staff, training on harmful chemicals and risk prevention | Provide necessary medical care. Safety checks throughout the site, implement further training | If a potential health concern is observed or has occurred. | QL
Site Unknowns (Site Conditions) | Accessibility of water for the equipment in operation. Conditions of soil for building/cleanup. | Schedule delay and cost. | 15% | 60000 | 9000 | Retain a geologist to study the site and water table. Identify utiltites from existing Civil/Survey plans. Retain a Geotechnical Engineer | Identify a different water source. Retain an additional Consultant. | Inaccessibility to feasible water sources. Nonideal conditions of the site for design. | QL
Competency (Quality) | Incompetency of the contractor hired by the owner. Misuse of equipment once it has been installed | Schedule delay, costs incurred, incorrect installation, increased liability. | 10% | 80000 | 8000 | Assisting owner in procurement phase. Ensure the user has the proper specifications and training for the operating phase. | Seeking alternative Contractors with the remainder of the performance bond. Replacing part or equipment that has been damaged. Employee training. | Lack of progress, improper installation of equipment, unnecessary change orders, overall incompetency. Equipment fails. | PM
Construction (Client/Stakeholder) | Client does not allow change orders without large justification. | Schedule delay. | 25% | 20000 | 5000 | Ensuring quantities during construction with a field representative of the Consultant. | Continue to support the client through the process and continue to monitor progress. | Client gives pushback to a potential or incoming change order. | PM
Incorrect Design and Performance (Client/Stakeholder) & (Technical/Scope) | Data utilized is provided entirely by the client. | Schedule delay and cost. | 20% | 40000 | 8000 | Have someone from the team double-check the data provided by the client. Researching all equipment to be specified and performing case studies. | Conducting meeting with client in order to discuss in detail the data provided. | Issues arise with existing site conditions, client's desire, equipment operation and chemical cleanup. | PM
Note on D6: probability of the risk occurring (% chance)
Note on E6: Potential impact in $. (your best assessment of overall impact)